## Sheet1
Defect ID | Description | Date Reported | Status | Assigned TO | Resolution | Target Resolution Date
DE-001 | Login form error (e.g., invalid credentials message not clear) | 2024-03-05 | Open | Developer A | Under Investigation | 2024-03-10
DE-002 | Cannot add item to cart (e.g., functionality not working) | 2024-03-04 | In progress | Developer C | Fix implemented,Testing in Progress | 2024-03-12
DE-003 | About in Navbar Redirecting to Home Page | 2024-03-03 | Fixed | QA Tester | Fixed Navbar,Redirecting Properly | 2024-03-11
DE-004 | Not Generating QR code for UPI Transaction | 2024-03-04 | New | Developer B | To be Assigned | 2024-03-14
Requirement ID | Requirement Description (Business Requirement / User Story) | Design Element | Test Case ID(s) | Defect ID(s)
BR-001 | Customers must be able to Register their account. | Registeration form | TC-001: Successful registration | DE-001: Registration form error
BR-002 | Customers must be able to log in to their accounts. | Login form | TC-002: Successful login | DE-002: Login form error (invalid credentials)
US-001 | As a customer, I want to have all classification of products in Navbar | Product category navigation | TC-003: Browse products by types | N/A
US-002 | As a customer, I want to know about the Top deals Today | Top Deals Today details | TC-004: View Top deals details | DE-003: Missing Price details
US-003 | As a customer, I want to add items to my shopping cart so I can purchase them later. | Shopping cart functionality | TC-005: Add item to cart | DE-006: cannot add more than 100 items
US-004 | As a customer, I want to view all the available payment options | Available Payment options | TC-007: Successful selected Payment method | DE-008: Not showing Netbanking Image
DSR | A defect report is a document that has concise details about what defects are identified, what action steps make the defects show up, and what are the expected results instead of the application showing error (defect) while taking particular step by step actions. Defect reports are usually created by the Quality Assurance team and also by the end-users (customers). Often customers detect more defects and report them to the support team of the software development since the majority of the customers curiously tries out every feature in the application. Now, you know what actually defect and defect reports are.
RTM | RTM stands for Requirement Traceability matrix. RTM maps all the requirements with the test cases. By using this document one can verify test cases cover all functionality of the application as per the requirements of the customer. Each test case is traced back to each requirement in the RTM. Therefore, there is less chance of missing any requirement in testing, and 100% test coverage can be achieved. RTM helps users discover any change that was made to the requirements as well as the origin of the requirement. Using RTM, requirements can be traced to determine a particular group or person that wanted that requirement, and it can be used to prioritize the requirement. It helps to keep a check between requirements and other development artifacts like technical and other requirements. The Traceability matrix can help the tester identify whether by adding any requirement previous requirements are affected or not. RTM helps in evaluating the effect on the QA team to reuse the test case.